Four Month Plan

Registration by Dec. 31, 2009

| Task or Task Group | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- |
| Gap Analysis | Sept. 6 |  |  |  |
| First Steering Team Meeting Assign Team Members | Sept 8 |  |  |  |
| Train Team Members | Sept 13 |  |  |  |
| Document Control Meet Weekly From: | Sept 13 to |  | Nov 8 |  |
| Control of Quality Records Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Management Responsibility Meet Weekly From: | Sept 13 to |  | Nov 8 |  |
| Competence, Awareness and Training Meet Weekly From: |  | Oct 4 to | Nov 8 |  |
| Infrastructure Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Planning of Product Realization Processes Meet Weekly From: | Sept 13 to |  | Nov 30 |  |
| Customer Related Processes Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Design and Development Meet Weekly From: | Sept 13 to |  | Nov 30 |  |
| Purchasing Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Control of Production and Service Provision Meet Weekly From: | Sept 13 to |  | Nov 30 |  |
| Identification and Traceability Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Customer Property Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Preservation of Product Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Control of Measuring and Monitoring Devices Meet Weekly From: | Sept 13 to |  | Nov 30 |  |
| Monitoring, Measuring and Analysis of Customer Satisfaction Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Internal Audits Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Monitoring, Measuring and Analysis of Product and Realization Processes Meet Weekly From: |  | Oct 4 to Oct 29 |  |  |
| Control of Nonconforming Product Meet Weekly From: |  | Oct 4 to | Nov 8 |  |
| Corrective Action and Preventive Action Meet Weekly From: |  |  | Nov 1 to Nov 30 |  |
| Start Internal Audits |  |  | Nov 30 |  |
| Hold Management Review |  |  | Dec 1 |  |
| Train all employees |  |  | Nov 15 to Nov 30 |  |
| Run system as each team completes, total system running by |  |  | Nov 30 |  |
| Registration Audit |  |  |  | Late Dec |