Seven Month Plan

Registration by June 30, 2009

| Task or Task Group | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Gap Analysis | Sept. 15 |  |  |  |  |  |  |  |  |  |
| First Steering Team Meeting Assign Team Members | Sept 22 |  |  |  |  |  |  |  |  |  |
| Train Team Members | Oct 1 To Oct 8 |  |  |  |  |  |  |  |  |  |
| Document Control Meet Weekly From: | Oct 11 to |  |  | Dec 22 |  |  |  |  |  |  |
| Control of Quality Records Meet Weekly From: |  | Oct 4 To | Nov 15 |  |  |  |  |  |  |  |
| Management Responsibility Meet Weekly From: | Oct 11 to |  |  | Dec 22 |  |  |  |  |  |  |
| Competence, Awareness and Training Meet Weekly From: |  | Oct 4 to | Nov 30 |  |  |  |  |  |  |  |
| Infrastructure Meet Weekly From: |  | Oct 4 to | Nov 15 |  |  |  |  |  |  |  |
| Planning of Product Realization Processes Meet Weekly From: | Oct 11 to |  |  |  | Jan 30 |  |  |  |  |  |
| Customer Related Processes Meet Weekly From: |  | Oct 4 to |  | Dec 22 |  |  |  |  |  |  |
| Design and Development Meet Weekly From: | Oct 11 to |  |  |  | Jan 30 |  |  |  |  |  |
| Purchasing Meet Weekly From: |  | Oct 4 to |  | Dec 15 |  |  |  |  |  |  |
| Control of Production and Service Provision Meet Weekly From: | Oct 11 to |  |  |  | Jan 30 |  |  |  |  |  |
| Identification and Traceability Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Customer Property Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Preservation of Product Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Control of Measuring and Monitoring Devices Meet Weekly From: | Oct 11 to |  |  | Dec 22 |  |  |  |  |  |  |
| Monitoring, Measuring and Analysis of Customer Satisfaction Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Internal Audits Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Monitoring, Measuring and Analysis of Product and Realization Processes Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Control of Nonconforming Product Meet Weekly From: |  |  |  |  | Jan 3 to |  | March 15 |  |  |  |
| Corrective Action and Preventive Action Meet Weekly From: |  |  |  |  |  | Feb 1 | March 15 |  |  |  |
| Start Internal Audits |  |  |  |  |  |  |  | April 4 |  |  |
| Hold Management Review |  |  |  |  |  |  |  | April 13 | May 18 | June 1 |
| Train all employees |  |  |  |  |  |  | March 15 to March 30 |  |  |  |
| Run system as each team completes, total system running by |  |  |  |  |  |  |  | April 1 |  |  |
| Registration Audit |  |  |  |  |  |  |  |  |  | Late March |